## Sheet1
Name | Owner | Scheduled State | Estimate | Task Remaining Total
Set Up Git on all machines | Cusuh H | In-Progress | 0.5 | 0.5
Carry out Version Control Lab | Ind. Assignment | Defined | 2 | 2
Create Build Files | Ind. Assignment | Defined | 2 | 2
Test Build Files | Ind. Assignment | Defined | 1 | 1
Create a Context Diagram for the System | Nick G | Defined | 2 | 2
Brainstorm and list 10 use cases | Joshua Winchester | Defined | 2 | 2
Each person pick 1 use case and fully detail it | Ind. Assignment | Defined | 5 | 5
Create Space Trader FX Project | Joshua Winchester | Defined | 2 | 2
Create opening screen | Omar M | Defined | 3 | 3
Transition to game configuration when "start game" is selected | Nick G | Defined | 3 | 3
Name and Skill Points | Cusuh H | Defined | 3 | 3
Accepting Dialog | Renee B | Defined | 3 | 3
Canceling Dialog | Renee B | Defined | 3 | 3
Brainstorm and Filtered Classes | Nick G | Defined | 1 | 1
Model appropriate classes | Nick G | Defined | 2 | 2
Annotate classes with appropriate stereotypes | Omar M | Defined | 2 | 2
Model shows multiplicity of associations | Joshua Winchester | Defined | 2 | 2
Model contains appropriate attributes | Omar M | Defined | 2 | 2
Player Configuration screen is integrated | Nick G | Defined | 2 | 2
Universe generates correctly | Nick G | Defined | 2 | 2
Game screen is displayed | Joshua Winchester | Defined | 2 | 2
All code is javadoc'd | Cusuh H | Defined | 1 | 1
Create a Page- Renee | Renee B | Completed | 1 | 0
Create a Page - Omar | Omar M | Completed | 1 | 0
Create a Page - Nick | Nick G | Completed | 1 | 0
Create a Page - Cusuh | Cusuh H | Completed | 1 | 0
Create a Page - Joshua | Joshua Winchester | Completed | 1 | 0
Come up with a Name | Cusuh H | Completed | 2 | 0
Assign Roles | Joshua Winchester | Completed | 1 | 0
Come up With Rules | Cusuh H | Completed | 1 | 0
Create a Peer Evaluation Form | Renee B | Completed | 1 | 0
Create Penalties | Cusuh H | Completed | 1 | 0
Sign and Agree | Ind. Assignment | Completed | 0.5 | 0
Create Sprint Backlog | Omar M | Completed | 2 | 0
Create Product Backlog | Joshua Winchester | Completed | 2 | 0
| Total hours |  | 63 | 47.5